## Sheet1
Requirements Traceability Matrix (RTM)
Requirement ID | Requirement Description | Priority Level (MoSCoW) | Stakeholder(s) | Project Objective | Related Data File | Status
FR1 | Automate appointment scheduling | Must Have | Patients, Admin Staff | Reduce patient wait times and scheduling errors | appointment_data.csv | In Progress
FR2 | Real-time notification system | Must Have | Patients, Doctors | Improve communication and reduce no-shows | feedback_data.csv | Planned
FR3 | Resource allocation dashboard | Should Have | Hospital Management | Optimize resource utilization during peak hours | resource_data.csv | Planned
FR4 | Integration with patient medical records | Should Have | Doctors, IT Team | Provide seamless access to patient history | appointment_data.csv | Not Started
NFR1 | Ensure HIPAA compliance | Must Have | Compliance Team, IT Team | Maintain legal and data privacy standards | N/A | In Progress
NFR2 | System scalability for 10,000+ patients | Could Have | IT Team, Hospital Management | Ensure system can handle growing patient demand | resource_data.csv | Not Started
NFR3 | 24/7 system availability | Must Have | Patients, Doctors, Admin | Ensure reliable system access for all users | appointment_data.csv | Plann